**A close up of a sign

Description automatically generated**

**Brinklow Roundabout**

**September update**

Over the past month, considerable progress has been made in completing most of the civil works, including ducting, chamber construction, NAL socket installations, and street lighting cable upgrades. The current focus is on preparing for resurfacing, due to commence on **8 September**, alongside the rollout of road markings, road studs, and traffic signal installations.

**Planned Programme of Works**

**SEPTEMBER**

**Night works (8pm – 5am) the roundabout will be closed.**

|  |  |  |
| --- | --- | --- |
| **DATE** | **TIME** | **ACTIVITY** |
| **8–12 September** | 8pm to 5am | Resurfacing, topsoiling, and signage works. |
| **15–19 September** | 8pm to 5am | Resurfacing, joint treatment, and road marking works |
| **15–19 September** | 8pm to 5am | Traffic signal equipment installation |
| **22–26 September** | 8pm to 5am | Traffic signal equipment installation |
| **22–26 September** | 8pm to 5am | Street lighting upgrades, road studs, and signal detection works |
| **29–30 September** | 8pm to 5am | Installation of four cantilever mast arms |

**Daytime works (under lane restrictions – roundabout will remain open)**  
*For safety reasons, temporary lane closures will remain in place full time during this period.*

|  |  |  |
| --- | --- | --- |
| **DATE** | **TIME** | **ACTIVITY** |
| **8–26 September** | Daytime | Bus stop improvements and hedgerow maintenance |
| **8 September – 3 October** | Daytime | Waterproofing of bridge decks to underpasses (outer and inner ring) |

We apologise for any inconvenience these essential works may cause and appreciate your patience and understanding.