## Sheet1
Mowing Route 2026 | Week ending 12.4.26
Highlighted green is where teams were located on Friday of the week
The Esates above the green show what Estates have been mowed on this cycle
The Estates below the green shows where the teams will go next.
The spreadsheet shows how many cuts (cycles) they have completed this season (March – October).
The length of each cycle can be varied due to the growth of the grass, weather (prolonged dry weather or persistent rain) and public holidays.
East | West | North 1 & 2 All |  | Rural | Grid Roads
Passmore | Knowlhill | Wolverton Mill / Industry |  | Haversham | Single roads | Dual Roads
Woughton on the green | Loughton | Wolverton + Old Wolverton |  | Little Linford | V1 | V6
Woughton Park | Great Holm | Wolverton South |  | Gayhurst | V2 | V7
Simpson | CrownHill | Greenleys |  | Stoke Goldington | V3 | V8
Walton Park | Whitehouse | Hodge Lea |  | Cold Brayfield | V4 | V11
Walton Hall & Walton Park | Shenley Church End | Kiln Farm |  | Newton Blossomville | V5 | H3
Caldecotte | Shenley Wood | Two Mile Ash |  | Clifton Reynes | V6 | H5
Tilbrook | Medbourne | Wymbush |  | Emberton | V7 | H6
Browns Wood | Grange Farm | Bradwell Abbey Industry |  | Filgrave | V8 | H8
Old Farm Park | Hazeley | Bradwell Village (Bradwell) |  | Lathbury | V10 | H9
Wavendon Gate + Tower Gate | OakHill | Stacey Bushes |  | Sherington | V11 | H10
Walnut Tree | Oxley Park | Bancroft |  | Chichley | H1 | Not started
Kentshill Park | CMK | Blue Bridge |  | Hardmead | H2
Kentshill | Cut 1 | Bancroft Park |  | Astwood | H4
Monkston |  | Stonebridge |  | Little Crawley | V9
Monkston Park |  | New Bradwell | Heelands | North Crawley | H5
Oakgrove |  | Oakridge Park | Rooksley | Moulsoe | H6
Middleton & MK Village |  | Bradville | Bradwell Com | Calverton & Wealds | H7
Kingston |  | Stantonbury | Conniburrow | Wavendon | H9
Brinklow |  | Stantonbury Fld | Downs Barn | Woburn sands | H10
Broughton gate |  | Great Linford | Downhead Park | Bow Brickhill | Cut 1
Brooklands |  | Tongwell | Willen Park | Little Brickhill | Started 23/4/26
Broughton |  | Giffard Park | Bolbeck Park | Cut 2
Atterbury |  | Blakelands / Tongwell Lake | Pennyland
Northfield |  | Redhouse Park | Neath Hill |  | Note: Grid roads Duals to commence 20th April due top Traffic management
Magna Park |  |  | Linford Wood
Eagle Farm |  | Newport Pagnell
Cut 1 |  | Cut 1